## Sheet1
milestone review
| Expected: | Actual: | Reason if not met:
Learn SQL | 2021-03-18 | 2021-03-18
Create Database | 2021-03-22 | 2021-03-22
Connect DB and Bot | 2021-03-20 | 2021-03-20
Create connection to host server | 2021-03-23 | 2021-03-27
Create all the commands | 2021-03-27 | 2021-04-10
Do input validation | 2021-04-10 | 2021-04-17
Test and debug in live server | 2021-04-17 | 2021-04-24
Add more functions based on demand and use | 2021-04-24 | … | In progress
Finalize everything and consider feedback | 2021-04-27 | … | In progress